## Instructions
IT Project Cost Estimation Tool - Instructions
Overview:
This cost estimation tool works along side the Project Charter to capture an early estimate of the expected costs for both project implementation and on-going operations. The costs included in this estimate are for all areas of the project and include resource estimates from both within and outside ITS. There are 3 worksheets in this workbook:
1. Instructions (This Page)
2. Cost Estimate - The tools for entering estimates and assumptions; this is what you fill out
3. Estimate Basis - The details behind the selection options for each of the estimate areas
The tool provides both the ability to define a low and high estimate as well as apply a variance factor based on confidence level to a single (low) estimate. Information detailed here informs the Cost Breakdown section of the Project Charter.
Completing the Estimate:
Each item in the estimate includes a description, 3 values from which to choose, and the selection of a low estimate and high estimate. The selection options are the same for both the low and high estimate columns. The options are starting suggestions based on the explanations defined in the "Estimate Basis" worksheet; If you don't have a value that you believe accurately represents the cost for your project, you also have the ability to enter your own value for any estimate. For each row/item to estimate do the following:
1. Review the Cost Item and Description (Columns A-C)
2. Select an estimate from the low estimate options OR enter your own value (Column D)
3. Select an estimate from the high estimate options OR enter your own value (optional) (Column E)
4. Make any notes about the estimate to help clarify assumptions (Column F)
After completing the above, answer the cost variance question to provide a level of confidence and validity to the estimate.
Total Implementation Costs and Total Annual Costs are calculated automatically.
Questions:
Information on the entire Project Management Lifecycle is available at pmo.gmu.edu. If you have questions or would like assistance completing this form, please contact the ITS Portfolio and Project Management Office at pmo@gmu.edu.
Template Version 20220131

## Cost Estimate
Project ID and Name |  |  |  | Description
Category | Cost Item | Description | Low Estimate | High Estimate (Optional) | Project Notes or Assumptions Related to Estimate
Software | License / Subscription Fees | Inclusive of all elements used in the Mason tech stack, not just new systems..
| Other Software Costs | Other software costs, such as a one time purchase fee
| Total Software Cost |  | 0 | 0
Hardware | Hosting Fees | Platform as a Service (PaaS), Infrastructure as a Service (IaaS) or other fees related to a third party hosting the solution or parts of the solution
| Hardware Procurement | Any additional techical hardware required for the solution. May include servers, switches, routers, or any other equipment needed either as the solution or on which to operate the solution
| Additional Materials | Any additional materials not included in the above categories required for implementation
| Total Hardware Cost |  | 0 | 0
Labor (Hours) | Project Management Hours | Includes documenting and faciliating the work to be done by the project including scope, schedule, issue tracking, and ensuring completion of tasks
| Business Analysis Hours | Includes requirements gathering definition and business process engineering of the solution. This is developing the clear understanding of the solution and what it will accomplish and how
| Design, Development, Configuration Hours | Includes the detailed system design and configuration of any software or solution and implementing that design. This is the technical implementation
| System Integration Hours | Includes the design and development of integrations between systems (e.g., Integrating with Banner, Salesforce, etc.)
| Testing and Verification Hours | Conducting system and user acceptance testing of the solution prior to release. Tasks to ensure that the requirements have been satisfied and the solution meets the needs defined in the scope
| Training and Communication Hours | Includes development of training, end user communications, service catalog entries, knowledge base, or other organizational change management related materials for implementation
| Cyber Security Hours | Inclusion of any security reviews or effort to ensure solution is vetted, approved and secure per IT security requirements
| Data Analysis, Architecture, Admin. Hours | Analysis and administration of data requirements used for implementation to ensure standard requests and use of infomration is documented and approved for use in environment
| Configuration Mgt. and Deployment Hours | Design, document, and implementation of the processes related to future management of changes to a system and deployment per the process
Other Labor Hours Not included above (Describe)
| Total Hours | Sum of the above labor categories for total estimated project labor hours | 0 | 0
| Estimated Mason Labor Rate ($/hour) | Fully loaded (salary + fringe benefits) hourly rate used for estimate of Mason Labor | 48 | 48
| Total Labor Cost |  | 0 | 0
Other | Total Other Services | Additional services that do not belong in other categorizations such as consulting services
Variance | Total Variance Factor | Select a percentage to reflect how much variance to add to your project estimate. The precentage will be added to the estimate total to provide an alternate to the Low Estimate/High Estimate range.
Total | Total Implementation Cost | Total of above categories for both the low and high project estimate | 0 | 0
|  | Total Cost plus Variance | 0
Annual / Ongoing Costs | Operations and Support | Mason staff labor to operate the solution in an on-going basis. Estimate by using the hourly rate for Mason labor above multiplied by an estimated total labor hours
| Hardware Maintenance | Annual cost to maintain hardware infrastructure for the solution (servers, other devices, etc.)
| Ongoing License / Subscription Fees | Annual license or subscription fees paid to 3rd party vendor to operate the solution. May include paid 3rd party support costs as well
| Software Maintenance | Costs for on-going software maintenance, updates and/or upgrades. Includes estimate for cost of internal Mason labor not included in Operations and Support above
Total | Total Annual Costs | Total of above categories for both the low and high project estimate | 0 | 0

## Estimate Basis
Category |  | Cost | Low Value | Medium Value | High Value | Notes/Assumptions | Potential Updates
Initial Implementation Costs | Software | License / Subscription Fees | 50000 | 1000000 | 2500000 | Inclusive of all elements used in the Mason tech stack, not just new systems. High estimate: Large CRM/SAAS, Many users across entire org Medium estimate: Low estimate: Small user base, specific use | 2nd highest nominal range between low / high estimates Must also harmonize/rectify with ongoing cost license / subscription fees POTENTIAL ACTIONS 1. Make clear this is 1st year fees only (would this change estimates?) 2. Reduce this category, and increase the complementary ongoing category 3. Split apart License / Subscription fees
|  | Other Software Costs | 20000 | 100000 | 500000 | Inclusive of all elements used in the Mason tech stack, not just new systems. Other software costs, such as a one time purchase fee High estimate: Larger software with many users Medium estimate: Low estimate: Small feature or addition | 2nd highest ratio of High / Low estimates POTENTIAL ACTIONS 1. Reduce high value and increase low value
| Hardware | Hosting Fees | 10000 | 100000 | 250000 | Based on MS Azure price estimation: https://azure.microsoft.com/en-us/pricing/calculator/#app-service01c4a195-421c-47b1-8fdb-4b53b83fa679 High estimate: Many servers necessary Medium estimate: Low estimate: Few servers/space needed | 1st highest ratio of High / Low estimates POTENTIAL ACTIONS 1. Reduce high value and increase low value
|  | Hardware Procurement | 10000 | 50000 | 100000 | High estimate: Many servers necessary Medium estimate: Low estimate: Few servers/space needed
|  | Additional Materials | 25000 | 50000 | 100000 | Additional physical components or materials High estimate: Medium estimate: Low estimate:
| Labor | Total Hours (Informational Only) | 960 | 4608 | 19200 | Estimate for total staffing of a project High estimate: 10 people, 100% dedicated, 12 months Medium estimate: 6 people, 80% dedicated, 6 months Low estimate: 4 people, 50% dedicated, 3 months | Highest nominal range between low / high estimates POTENTIAL ACTIONS 1. Reign in overall ranges, reducing high and increasing low estimates 2. Add in more guiding factors on what constitutes a Low / Medium / High
|  | Project Management Hours | 96 | 480 | 1536 | High estimate: 1 person, 80% dedicated, 12 months Medium estimate: 1 person, 50% dedicated, 6 months Low estimate: 1 person, 20% dedicated, 3 months
|  | Business Analysis Hours | 360 | 1920 | 7040 | Includes requirements gathering definition and business process engineering High estimate: 5 people, 80% dedicated, 11 months Medium estimate: 3 people, 80% dedicated, 5 months Low estimate: 1 person, 75% dedicated, 3 months | GUIDING FACTORS: Low: Affects at most 1 medium to large business process Medium: Affects at most 4 medium to large business processes High: Affects more than 4 business processes
|  | Design, Development, Configuration Hours | 240 | 1680 | 6600 | High estimate: 5 people, 75% dedicated, 11 months Medium estimate: 3 people, 70% dedicated, 5 months Low estimate: 1 person, 50% dedicated, 3 months | GUIDING FACTORS: Low: Minor modification of one existing system Medium: Significant modification of one system, or implementation of one new low to medium complexity system High: Significant modification of multiple system, or implementation of one or more high complexity systems or multple low to medium complexity systems
|  | System Integration Hours | 80 | 320 | 720 | Broke apart from Design, Dev, Config to have visibility into integration costs High estimate: 2 people, 75% dedicated, 3 months Medium estimate: 2 people, 50% dedicated, 2 months Low estimate: 1 person, 50% dedicated, 1 month | GUIDING FACTORS: Low: Simple integration to one system Medium: Simple to moderately complex integration with one or multiple systems High: Requires new framework for integration with multiple systems
|  | Testing and Verification Hours | 96 | 320 | 1280 | High estimate: 2 people, 50% dedicated, 8 months Medium estimate: 2 people, 50% dedicated, 2 months Low estimate: 1 person, 30% dedicated, 2 month
|  | Training and Communication Hours | 40 | 160 | 320 | High estimate: 2 people, 50% dedicated, 3 months Medium estimate: 2 people, 25% dedicated, 3 months Low estimate: 1 person, 25% dedicated, 1 month
|  | Cyber Security Hours | 80 | 256 | 960 | High estimate: 2 people, 50% dedicated, 6 months Medium estimate: 2 people, 40% dedicated, 2 months Low estimate: 1 person, 50% dedicated, 1 month
|  | Data Analysis, Architecture, Admin. Hours | 80 | 256 | 960 | High estimate: 2 people, 50% dedicated, 6 months Medium estimate: 2 people, 40% dedicated, 2 months Low estimate: 1 person, 50% dedicated, 1 month
|  | Configuration Mgt. and Deployment Hours | 40 | 120 | 320 | High estimate: 2 people, 50% dedicated, 3 months Medium estimate: 2 people, 25% dedicated, 3 months Low estimate: 1 person, 25% dedicated, 1 month
|  | Other Labor Hours | 80 | 256 | 960 | High estimate: 2 people, 50% dedicated, 6 months Medium estimate: 2 people, 40% dedicated, 2 months Low estimate: 1 person, 50% dedicated, 1 month | Other groups not included in the baseline
|  | Other Services | 50000 | 100000 | 250000 | Additional services that do not belong in other categorizations Hidden in Worksheet
Ongoing Costs |  | Operations and Support | 20000 | 50000 | 150000 | Labor needed to keep things running High estimate: Medium estimate: Low estimate:
|  | Hardware Maintenance | 20000 | 50000 | 150000 | Maintenance of servers and other devices High estimate: Medium estimate: Low estimate:
|  | Ongoing License / Subscription Fees | 20000 | 50000 | 150000 | Ongoing subscription fees | See License / Subscription Fees for Implementation Costs
|  | Software Maintenance | 20000 | 50000 | 150000 | Software upgrades in order to keep up High estimate: Medium estimate: Low estimate:
|  | Initial Cost Sum | 226200 | 1851200 | 5423600
Variance Estimates |  | No Variance | 0%
|  | Very Confident | 10%
20%
|  | Somewhat Confident | 30%
40%
|  | Moderately confident | 50%
60%
70%
|  | Not very confident | 80%
90%
|  | Little to no confidence | 100%
Labor Rates |  | Assumed Avg Labor Rate Internal (Hourly + Fringe) | 48
|  | Assumed Avg Labor Rate Contractor (Hourly) | 100